Website Proposal 2 of 2

Kgotso Community Library and Learning Hub

A seven-page website with online donations, volunteer sign-up and an events calendar — prepared by Asemahle, WEDE5020 Portfolio of Evidence, Part 2.

| Field | Detail |
| --- | --- |
| Client | Kgotso Community Library and Learning Hub, 88 Tsamaya Avenue, Mamelodi East, Pretoria |
| Organisation type | Registered non-profit organisation, NPO 214-889, with Section 18A tax status |
| Prepared by | Asemahle — Diploma in Software Development, IIE Rosebank College |
| Proposal reference | KCL-WEB-001 (submitted alongside Proposal 1, ref JPS-WEB-001, for a different client) |
| Date issued | 12 January 2026 |
| Valid until | 13 March 2026 |
| Proposed start | Monday 2 February 2026 |
| Proposed launch | Friday 3 April 2026 |
| Total Year 1 cost | R21 978 (excluding VAT — supplier is not VAT registered) |
| Build effort | 62 hours across nine calendar weeks |

# Executive summary

Kgotso Community Library and Learning Hub has run out of a converted church hall in Mamelodi East since 2017. It lends books, runs after-school homework support for roughly 140 learners a week, operates an eight-station computer lab, and teaches adult literacy on Saturday mornings. It does all of this on donor funding that is renegotiated every year, and it has no website.

That last point is now costing the organisation money. Corporate social investment officers cannot verify an organisation that does not exist online, and two grant applications in 2025 were returned unassessed for exactly that reason. Volunteers are recruited by WhatsApp forward, and donations arrive by EFT with no reference, which makes Section 18A receipting a manual reconstruction at the end of every tax year.

This proposal recommends a seven-page website built in HTML5 and CSS3, with three jobs to do: prove the organisation is real and accountable, make it possible to donate in under a minute, and let a volunteer sign up without anybody having to answer a phone.

The total first-year cost is R21 978 after a 20% non-profit discount on development, and the site goes live nine weeks after sign-off. Year two onwards runs at R7 758.

Relationship to Proposal 1. The two proposals in this portfolio are for different organisations and are offered as alternative projects, not as two versions of the same site. Proposal 1 covers John’s Plumbing Services, a commercial plumbing contractor whose site exists to convert search traffic into booked jobs. This proposal covers a non-profit whose site exists to establish credibility with funders and lower the friction on donating and volunteering. The audiences, the success measures and the content models are different throughout. A comparison and a build recommendation appear in section 11.

# 1.  Organisation overview

## 1.1  Background

Kgotso Community Library and Learning Hub was founded in March 2017 by Nomvula Sithole, a retired school librarian, after the nearest public library branch cut its opening hours to three days a week. It began as 400 donated books on trestle tables in a church hall. It is now a registered non-profit organisation with four paid staff, eleven regular volunteers, roughly 6 800 books on the shelves and 340 registered members.

The organisation is funded by a mix of corporate social investment grants, a small municipal subsidy, and individual donations. Grant income accounted for 71% of the 2025 budget, which is a concentration risk the board has asked to reduce.

## 1.2  Mission

To keep a free, safe, well-stocked place to read and study within walking distance of every child in Mamelodi East, and to make sure nobody leaves it still unable to read.

## 1.3  Vision

A Mamelodi in which library membership is ordinary rather than exceptional, and in which the matric pass rate in the surrounding four schools rises because there was somewhere to do the homework.

## 1.4  What the organisation does

| Programme | When | Who it serves |
| --- | --- | --- |
| Book lending | Mon – Sat | 340 registered members, all ages, free of charge |
| After-school homework support | Mon – Thu, 14:00 – 17:00 | Roughly 140 learners a week, Grades 4 to 11 |
| Computer and digital skills lab | Mon – Fri, by booking | Eight stations; job seekers, students and adult learners |
| Adult literacy classes | Saturday, 09:00 – 12:00 | Two groups of 15, taught by trained volunteers |
| School holiday reading programme | April, July and December | Roughly 200 children per holiday |
| Matric study camp | September and October | 60 Grade 12 learners from four feeder schools |

## 1.5  Target audiences

A non-profit website has to speak to two groups who want completely different things from the same pages. The design has to serve both without either feeling like an afterthought.

| Audience | What they need | What the site must do |
| --- | --- | --- |
| CSI and grant officers | Proof the organisation is real, registered and accountable before they will even open an application | Publish the NPO number, Section 18A status, board members, annual report and audited figures where a desk assessor will find them in under a minute |
| Individual donors | A way to give that takes less than a minute and produces a tax certificate | One prominent donate route, clear amounts tied to real outcomes, an explanation of Section 18A |
| Prospective volunteers | To know what is actually being asked of them before they commit | Role descriptions with real time commitments, a short sign-up form, no telephone gatekeeping |
| Parents and learners | Opening hours, what is on, and whether it costs anything | Programme pages and an events calendar written in plain language, readable on a cheap phone |
| Local schools and partners | A contact point and something to hand to their own governing body | A printable one-page overview and clear contact details |

# 2.  Website goals and objectives

## 2.1  Organisational goals

- Pass the desk-assessment stage of grant applications by publishing registration details, governance information and an annual report that an officer can verify without contacting anybody.

- Raise the share of income coming from individual donations from 6% to 15% of the annual budget within twelve months, reducing dependence on three large grants.

- Recruit 20 new volunteers a year through the site rather than through WhatsApp forwards, and reduce the drop-out rate by publishing honest role descriptions up front.

- Cut the Section 18A receipting workload by giving every online donation a reference number and a captured email address at the point of donating.

- Give parents a single reliable source for opening hours and holiday programme dates, replacing the printed notices that go out of date within a week.

## 2.2  Key performance indicators

| Indicator | Baseline today | Target, month 12 | How it is measured |
| --- | --- | --- | --- |
| Monthly unique visitors | 0 | 1 200 | Google Analytics 4 |
| Online donations per month | 0 | 35 | Payment gateway dashboard |
| Individual giving as share of income | 6% | 15% | Annual financial statements |
| Volunteer applications per month | 2 (by WhatsApp) | 8 (via the form) | Form submission counter |
| Grant applications reaching assessment | 3 of 5 in 2025 | 5 of 5 | Board grant register |
| Annual report downloads | 0 | 120 per year | Analytics file-download event |
| Average page load, 3G mobile | n/a | Under 2.5 seconds | Lighthouse, throttled |

# 3.  Current online presence — analysis

## 3.1  Strengths

- Nine years of continuous operation, a registered NPO number and Section 18A approval — the three things a funder checks first, all of which currently exist only on paper.

- An active Facebook page with 2 100 followers, mostly local parents, which posts holiday programme photographs and gets genuine engagement.

- Audited annual financial statements going back to 2019, prepared pro bono by a Pretoria accounting firm.

- A strong archive of photographs from holiday programmes and the matric study camp, taken with consent forms already signed.

- Measurable outcomes the organisation can point to: attendance registers, a lending log and feeder-school matric results.

## 3.2  Weaknesses

- No website, so a search for the organisation returns the Facebook page and a stale entry on a defunct NPO directory.

- Two 2025 grant applications were returned unassessed because the funder’s desk check could not verify the organisation online.

- Donations arrive by EFT with references like “donation”, so matching a payment to a donor for Section 18A purposes takes the bookkeeper a full day each February.

- Volunteer recruitment depends on a WhatsApp message being forwarded, which reaches people who already know the organisation and nobody else.

- Opening hours and holiday dates live on a printed A4 notice on the door and in three contradictory Facebook posts.

- The annual report exists as a 14 MB PDF emailed on request, which means it is almost never read.

## 3.3  Opportunities for improvement

- Put the NPO number, Section 18A status, board list and annual report on one accountability page. This is cheap to build and it is the single highest-value page on the site for funders.

- Tie donation amounts to concrete outcomes — R150 buys one school reader, R500 keeps the computer lab open for a day — which measurably improves conversion over an empty amount box.

- Publish honest volunteer role descriptions with real time commitments, so the people who apply are the people who stay.

- Build mobile first and keep the pages light. The audience is on prepaid data and mid-range Android handsets, so page weight is an access issue, not a performance nicety.

- Apply for the Google Ad Grant, which gives registered non-profits a monthly search advertising allowance at no cost — but it requires a functioning website first.

# 4.  Proposed features and functionality

## 4.1  Page-by-page scope

| Page | File | Contents and functionality |
| --- | --- | --- |
| Home | index.html | Hero stating what the hub is and where; three headline impact figures; summary of the six programmes; the next three upcoming events; a donor testimonial; donate and volunteer calls to action. |
| About | about.html | Founding story; mission, vision and values; staff and board profiles; the accountability block — NPO number, Section 18A status, auditor, annual report download. |
| Programmes | programmes.html | Jump navigation; six programme articles each with times, age range, cost and how to join; a summary table of the weekly timetable. |
| Events | events.html | Upcoming events listed with dates, times and booking notes; a past-events archive; a downloadable term calendar. |
| Get involved | get-involved.html | Four volunteer role descriptions with real time commitments; a book and equipment donation list; a volunteer sign-up form. |
| Donate | donate.html | Suggested amounts tied to outcomes; EFT banking details with a reference generator explained; Section 18A explanation; a recurring-giving option. |
| Contact | contact.html | Address, telephone, opening hours, a map placeholder, an enquiry form and a short FAQ. |

## 4.2  Site-wide features

- Responsive layout with four breakpoints — 36em, 48em, 64em and 80em — moving from a single column on a phone to three or four columns on a desktop.

- A navigation menu that collapses behind a button on small screens, built entirely in CSS with no JavaScript dependency.

- A persistent Donate link styled as a button in the header of every page, because it is the one action the site is measured on.

- Responsive images using srcset and sizes, so a mid-range Android phone downloads a 400-pixel file rather than a 1200-pixel one.

- Impact figures presented as a description list rather than as images of numbers, so they are readable, selectable and translatable.

- A print stylesheet, so the About page prints as a one-page organisational overview a school governing body can file.

- Accessibility built in: skip link, visible keyboard focus, labelled form controls, semantic landmarks and text that survives being enlarged to 200%.

## 4.3  Explicitly out of scope for this phase

- Server-side processing. The volunteer and enquiry forms are built and validated in the browser in this phase; the PHP handler is scheduled for Part 3.

- A hosted payment gateway integration. Phase one publishes EFT details and a reference convention; the gateway is quoted as an optional extra in section 9.3.

- An online library catalogue or member lending portal. The lending log stays on the desk for now.

- A member login area, a blog, or a multilingual version. Sepedi and isiZulu translations are recommended for a later phase once the English content has settled.

# 5.  Design and user experience

## 5.1  Colour palette

The palette is deliberately warm rather than corporate. The organisation is a place children walk into after school, and a clinical blue-and-white scheme would misrepresent it. All foreground and background pairings meet the WCAG 2.1 AA contrast ratio of 4.5:1 for body text.

| Colour | Hex | Role | Rationale |
| --- | --- | --- | --- |
| Deep green | #1F5C3A | Header, footer, headings, primary buttons | Growth and steadiness; also the colour already used on the hub’s signage |
| Ochre | #E0A83C | Accents, the donate button, active navigation | Warm and visible; reserved for the actions that matter most |
| Terracotta | #C25B3A | Impact figures and event dates | A second accent so donate never competes with anything else |
| Cream | #FBF7EF | Page background | Softer than white on a cheap screen in a bright room |
| Charcoal | #22282B | Body text | Reads more kindly than pure black on a cream background |
| Stone | #6E7A72 | Secondary text and captions | Supports the hierarchy without competing with it |

## 5.2  Typography

| Role | Typeface | Treatment |
| --- | --- | --- |
| Headings | Bitter, 600 and 700 | A slab serif — it reads as books and reading rather than as a technology company. Fluid scale using clamp(), 1.75rem to 2.5rem |
| Body copy | Source Sans 3, 400 | 1rem on phones, 1.0625rem from 48em, 1.125rem from 80em; line height 1.7 because a lot of this audience reads slowly by choice or by circumstance |
| Impact figures | Bitter, 700 | 3rem, in terracotta, paired with a plain-language label beneath |
| Measure | — | Paragraphs capped at 62 characters using the ch unit |
| Units | — | rem for type, em for component padding, % for widths |

## 5.3  Layout approach

- Mobile first. The stylesheet describes the phone layout, and min-width media queries add columns as the screen grows.

- CSS Grid for page structure and card grids; Flexbox for one-dimensional rows such as the navigation bar and button groups.

- A centred content wrapper at 90% of the viewport width with a 72rem ceiling.

- Content order is written once in the HTML, in reading order. The stylesheet never reorders it — it only changes how many columns that content flows into.

## 5.4  User experience principles

- Two audiences, one page each. Funders are served by the About page; donors and volunteers are served by Donate and Get involved. Neither is made to wade through the other’s content.

- Donate is reachable from the header of every page, in one tap, on any screen size.

- Every number on the site is dated and sourced. An impact figure with no date is a claim; one with a date is evidence.

- Plain language throughout. If a sentence would not be understood by a Grade 9 learner, it is rewritten.

- The site works with JavaScript switched off, and it works on a 3G connection.

## 5.5  Wireframes

The wireframe pack submitted with this portfolio was produced for the Proposal 1 site. If this proposal is the one taken forward, an equivalent pack of ten annotated wireframes would be produced in week 2 of the schedule in section 8, covering all seven pages at desktop width, the home and donate pages at mobile width, a breakpoint behaviour diagram and a site map diagram. The two hours for that work are already carried in the week 2 line.

# 6.  Technical requirements

| Item | Specification |
| --- | --- |
| Domain | kgotsolibrary.org.za — the .org.za namespace is conventional for South African non-profits and carries a small credibility benefit with funders |
| Hosting | Shared Linux hosting, 10 GB SSD storage, 50 GB monthly transfer, South African data centre |
| Certificate | Let’s Encrypt TLS certificate, auto-renewing, included at no cost by the host |
| Markup | HTML5, semantic elements throughout, validated against the W3C Nu validator with zero errors |
| Styling | CSS3 in a single external stylesheet (css/style.css); custom properties, Grid, Flexbox, clamp() and min-width media queries |
| Scripting | None required in this phase. The navigation, accordions and form validation are all native HTML and CSS |
| Forms | HTML5 validation in this phase; a PHP handler with honeypot spam protection scheduled for Part 3 |
| Documents | Annual report supplied as a compressed PDF under 2 MB, with the file size stated next to the download link |
| Images | JPEG and WebP, three widths per hero image and two per gallery image, served with srcset and sizes |
| Data protection | POPIA-compliant privacy notice; volunteer form collects the minimum necessary and states the retention period |
| Consent | No photograph of an identifiable child is published without a signed consent form on file |
| Browsers | Chrome, Edge, Firefox and Safari, current and one previous version; Samsung Internet on Android |
| Devices tested | 360×640, 390×844, 768×1024, 1366×768 and 1920×1080 |
| Accessibility | WCAG 2.1 level AA as the working target |
| Version control | Git, hosted on GitHub at github.com/mahleSoftdev, with a commit per completed unit of work |
| Analytics | Google Analytics 4 with events on the donate route, the volunteer form and the annual report download |

# 7.  Content plan

Content is the usual reason a non-profit website is late. This section names who produces what and by when, so that the schedule in section 8 has something to stand on.

| Content item | Produced by | Needed by | Notes |
| --- | --- | --- | --- |
| Impact figures for 2023 – 2025 | Hub administrator | Fri 13 Feb 2026 | Attendance registers and lending log; every figure needs a date |
| Board member list and short biographies | Board secretary | Fri 13 Feb 2026 | Names, roles and dates appointed |
| Annual report 2025, compressed | Accountant | Fri 20 Feb 2026 | Under 2 MB; file size stated next to the link |
| Programme descriptions, six | Programme coordinators | Fri 20 Feb 2026 | Times, age range, cost, how to join |
| Volunteer role descriptions, four | Volunteer coordinator | Fri 27 Feb 2026 | Honest time commitments, not aspirational ones |
| Photographs with consent on file | Hub administrator | Fri 27 Feb 2026 | No identifiable child without a signed form |
| Term and holiday programme dates | Hub administrator | Fri 6 Mar 2026 | Needed before the Events page can be finished |
| Banking details and reference convention | Treasurer | Fri 6 Mar 2026 | Confirmed with the bank before publication |

# 8.  Timeline and milestones

The build is 62 hours of effort delivered across nine calendar weeks, working part time. Dates assume sign-off on Friday 30 January 2026 and content supplied on the dates in section 7. Each week ends with something the board can look at.

## 8.1  Week-by-week schedule

| Week | Dates | Activity | Deliverable | Depends on | Hrs |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 – 6 Feb | Discovery, stakeholder interviews, content audit, information architecture | Approved content plan and page inventory | Signed proposal | 6 |
| 2 | 9 – 13 Feb | Site map, ten wireframes, repository setup, folder structure | Site map + wireframe pack signed off | Week 1 | 6 |
| 3 | 16 – 20 Feb | Home and About pages, including the accountability block | Two pages viewable in a browser | Impact figures and board list | 9 |
| 4 | 23 – 27 Feb | Programmes and Events pages, timetable table, event listings | Four pages complete | Programme descriptions | 9 |
| 5 | 2 – 6 Mar | Get involved and Donate pages, volunteer form, giving tiers | Six pages complete | Role descriptions; banking details | 9 |
| 6 | 9 – 13 Mar | Contact page; stylesheet foundation — reset, tokens, typography, chrome | All seven pages built; site chrome styled | Week 5 | 7 |
| 7 | 16 – 20 Mar | Components and the four responsive breakpoints | Fully styled responsive site on staging | Week 6 | 7 |
| 8 | 23 – 27 Mar | Content load, image optimisation, accessibility pass, cross-browser testing | Test report and defect log cleared | All content supplied | 5 |
| 9 | 30 Mar – 3 Apr | Deployment, DNS cutover, analytics, staff training session | Live site + 90-minute training | Week 8; domain delegated by 27 Mar | 4 |

Total effort: 62 hours.

## 8.2  Milestones and approval gates

| Milestone | Date | What is delivered | Client action required |
| --- | --- | --- | --- |
| M1 — Kick-off | Fri 30 Jan 2026 | Signed proposal and deposit received | Board resolution, signature, 40% deposit |
| M2 — Structure agreed | Fri 13 Feb 2026 | Site map and ten wireframes | Approve or request changes within 5 working days |
| M3 — Content cut-off | Fri 6 Mar 2026 | All items in the section 7 content plan received | Supply all assets — late content moves the launch date |
| M4 — Draft site | Fri 13 Mar 2026 | All seven pages built, chrome styled | Review content accuracy, especially the figures |
| M5 — Styled site | Fri 20 Mar 2026 | Responsive styled site on a staging link | Review on a phone and a desktop; pay 30% |
| M6 — Test sign-off | Fri 27 Mar 2026 | Test report, defect log closed | Approve for launch; delegate the domain |
| M7 — Launch and training | Fri 3 Apr 2026 | Live site, analytics, 90-minute staff training | Final 30% payment within 14 days |

## 8.3  Schedule assumptions

- Board approval is a scheduled meeting rather than a single signature, so five working days are allowed at M2 instead of three.

- All content in section 7 arrives by Friday 6 March. If it does not, affected pages launch with placeholder text and are updated afterwards at no extra cost.

- The domain is delegated to the nominated nameservers by Friday 27 March so DNS propagation completes before launch day.

- One round of revisions is included at each of M2, M4 and M5. Further rounds are billed at the hourly rate in section 9.

- The 90-minute training session covers editing text, swapping photographs and adding an event. It is recorded so new staff can watch it later.

# 9.  Budget

All figures are in South African Rand and exclude VAT. The supplier is not VAT registered, so no VAT is charged. Third-party costs — domain, hosting and email — are billed at cost with no mark-up. A 20% non-profit discount is applied to development labour.

## 9.1  Year 1 — setup and build

| Line item | Basis | Qty | Rate | Amount |
| --- | --- | --- | --- | --- |
| Domain registration, .org.za | Annual registration fee | 1 yr | R150 | R150 |
| Shared Linux hosting with SSL | 10 GB SSD, 50 GB transfer, free TLS | 12 mo | R89 | R1 068 |
| Business email mailboxes | info@, volunteer@ and donations@ | 36 mo-boxes | R35 | R1 260 |
| Website design and build | Seven pages, hand-coded, responsive | 62 hrs | R220 | R13 640 |
| Photography | Half-day on site, 15 edited images, consent checked | 1 | R2 200 | R2 200 |
| Copywriting and proofreading | Seven pages of plain-language copy | 7 pages | R280 | R1 960 |
| Logo redraw and brand kit | Vector redraw, favicon set, social header | 1 | R1 400 | R1 400 |
| Annual report compression and layout | 14 MB PDF reduced below 2 MB, bookmarked | 1 | R650 | R650 |
| Google for Nonprofits and Ad Grant application | Verification, account setup, first campaign | 1 | R750 | R750 |
| Subtotal before discount |  |  |  | R23 078 |
| Non-profit discount | 20% of development labour |  |  | – R2 728 |
| Subtotal |  |  |  | R20 350 |
| Contingency | 8% of subtotal, for scope movement |  |  | R1 628 |
| TOTAL YEAR 1 |  |  |  | R21 978 |

## 9.2  Year 2 onwards — running costs

| Line item | Basis | Frequency | Annual |
| --- | --- | --- | --- |
| Domain renewal | .org.za registration | Annual | R150 |
| Hosting and SSL | Same shared plan | Monthly | R1 068 |
| Business email | Three mailboxes | Monthly | R1 260 |
| Maintenance retainer | Event updates, content edits, backup checks, 2 hrs per month | Monthly | R5 280 |
| TOTAL PER YEAR |  |  | R7 758 |

The Google Ad Grant, if the application in 9.1 succeeds, provides up to USD 10 000 per month in search advertising at no cost. It is not counted as income here because it is not guaranteed.

## 9.3  Optional extras, quoted separately

| Item | What it adds | Once-off |
| --- | --- | --- |
| Payment gateway integration | Card and instant-EFT donations through a South African gateway, with automatic reference numbers | R2 400 |
| PHP form handler and thank-you page | Volunteer and enquiry forms email the office directly (Part 3 scope) | R1 450 |
| Recurring donation setup | Monthly debit order mandate form and gateway configuration | R1 100 |
| Sepedi and isiZulu translation of key pages | Home, Programmes and Get involved in two additional languages | R3 600 |
| Online library catalogue | Searchable listing of the 6 800-book collection | R4 800 |

Note on gateway fees: South African donation gateways charge roughly 2.95% plus R1 per transaction. On a R150 donation that is about R5.43. These are transaction costs borne by the organisation and are not part of the build budget.

## 9.4  Payment schedule

| Stage | Share | Amount | Trigger |
| --- | --- | --- | --- |
| Deposit | 40% | R8 791 | On signature, Friday 30 January 2026 |
| Progress payment | 30% | R6 593 | At M5, styled site on staging, 20 March 2026 |
| Final payment | 30% | R6 594 | Within 14 days of launch, 3 April 2026 |

Payment by electronic funds transfer. Fourteen days are allowed on the final invoice rather than the usual seven, because non-profit payment runs are tied to board meetings. Ownership of the code and content transfers to the organisation on receipt of the final payment.

# 10.  Risks and mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Content arrives late from volunteers | High | High | Section 7 names one person per item with a date; affected pages launch with placeholders and are updated free of charge |
| Board approval cycles delay decisions | High | Medium | Five working days allowed at each gate; approvals scheduled to fall after the monthly board meeting |
| Consent for a child’s photograph cannot be evidenced | Medium | High | No identifiable child is published without a signed form on file; a stock of consented images is agreed in week 1 |
| Impact figures cannot be substantiated | Medium | High | Every published figure carries a date and a source; anything unverifiable is cut rather than rounded |
| Funding for year-two running costs is not secured | Medium | High | Annual cost is R7 758; a single line item is written into the next grant application, and hosting is paid annually in advance |
| Staff cannot update the site after handover | High | Medium | Two hours a month of edits in the retainer, plus a recorded 90-minute training session and a written guide |
| Load shedding interrupts the build | High | Low | Work is version-controlled in Git and pushed after each unit of work, so nothing is lost |

# 11.  The two proposals compared

The portfolio contains two proposals for two unrelated organisations. They are alternatives, not variations. This section sets them side by side so the choice of which to build is a reasoned one.

| Factor | Proposal 1 — John’s Plumbing Services | Proposal 2 — Kgotso Community Library |
| --- | --- | --- |
| Sector | Commercial services, for-profit | Registered non-profit organisation |
| Primary purpose | Convert search traffic into booked jobs | Establish credibility with funders; lower friction on donating and volunteering |
| Primary audience | Homeowners and property managers in Pretoria East | CSI officers, individual donors, volunteers, parents and learners |
| Pages | Six | Seven |
| Conversion action | Book a plumber | Donate, and sign up as a volunteer |
| Headline success measure | Bookings per month | Individual giving as a share of annual income |
| Content model | Services, indicative prices, job photographs, testimonials | Programmes, events calendar, impact figures, governance and accountability |
| Distinctive feature | Published price table with duration and guarantee columns | Accountability block — NPO number, Section 18A status, auditor, annual report |
| Tone and palette | Navy and bright blue; clean, professional, utility-like | Deep green, ochre and cream; warm, slab-serif headings |
| Build effort | 55 hours over eight weeks | 62 hours over nine weeks |
| Year 1 cost | R16 620 | R21 978 after a 20% non-profit discount |
| Year 2 onwards | R7 620 | R7 758 |
| Main risk | Photographs arrive late | Content arrives late from volunteers, and board approval cycles |

## 11.1  Recommendation for this portfolio

Proposal 1 is recommended as the site to build for WEDE5020 Part 2. Two reasons, and neither is about which organisation deserves a website more.

- Content availability. The plumbing site can be written from a service list and a price sheet. The library site depends on impact figures, board biographies, a compressed annual report and photographic consent — eight content items from six different people. Within a 55-hour academic budget, waiting on content is a risk that cannot be mitigated.

- Assessment fit. The module is assessed on semantic structure, layout, responsive CSS and organisation. A six-page commercial site with a price table, two forms and a service catalogue exercises every one of those criteria without needing a payment gateway or a document library, both of which sit outside the scope of Part 2.

Proposal 2 remains the stronger project in terms of social value, and it is documented here to the same standard so it could be picked up and built in a later phase, or as a Part 3 extension, without restarting the planning work.

# 12.  Acceptance

Signing below accepts the scope in section 4, the content plan in section 7, the schedule in section 8 and the costs in section 9.

| For Kgotso Community Library and Learning Hub | For the supplier |
| --- | --- |
| Name: ______________________________ | Name: Asemahle |
| Position: ___________________________ | Position: Web developer |
| Signature: __________________________ | Signature: __________________________ |
| Date: _______________________________ | Date: _______________________________ |

Proposal KCL-WEB-001  |  Issued 12 January 2026  |  Valid until 13 March 2026